Fiscal Year (FY) 2016 Timeline for ACEP: Entering into New Agreements and Obligations and Deadlines for Prior Year Agreements - REVISED

| ACEP FY 2016 Enrollment Actions | Completion Date* | Notes |
| --- | --- | --- |
| ACEP-WRE: Submission of FY 2016 easement compensation packages for ACEP-WRE to the EPD Sharepoint Site in the State folder at “FY 2016 GARCs-ACEP-WRE.” | October 1, 2015 | FY 2016 ACEP-WRE easement compensation packages must be submitted by all States, regardless of whether AWMA or individual USPAP appraisals will be used. |
| Guidance and allocations for ACEP implementation in FY 2016 provided to States. | On or about October 1, 2015 | Enter SCIMS and NEST data as soon as possible for all eligible applications. |
| States review all ACEP regulations, policy and FY 2016 guidance. | October 15, 2015 | Prepare State materials and updates as needed. |
| Update State ranking criteria and documents as needed. | November 2, 2015, no later than December 15, 2015 | Post FY 2016 ranking criteria to State Web sites and EPD SharePoint site in the “FY 2016 ACEP Ranking Worksheets” folder |
| States announce availability of ACEP funding and any FY 2016 application cutoff dates. | TBD - Pending Secretary Announcement | States should conduct ranking and eligibility determinations as soon as applications are received. State announcements should be published only after the National announcement. |
| Complete procurement of easement boundary surveys for FY 2015 ACEP-WRE enrollments. | December 31. 2015 | All contracts, orders, or agreements needed to obtain ACEP-WRE easement boundary surveys for prior year ACEP-WRE enrollments should be in place by this deadline. |
| For FY 2015 ACEP-WRE applications using individual USPAP appraisals that were authorized for carryover that require national-level internal control review: Complete State-level first- and second-level reviews, and upload documents and submit NEST maintenance request. | December 31, 2015 | Participants must be determined eligible in FY 2016 and must use EPD-approved FY 2016 easement compensation values as basis for the offer in the ACEP-WRE agreement. |
| National ACEP application cutoff for FY 2016 funding consideration. | January 15, 2016 | States may establish earlier cutoff dates based on workload but must provide at least 30 days from the announcement of fund availability |
| Fund obligation deadline for FY 2015 ACEP-WRE individual USPAP appraisal applications authorized for carryover | January 31, 2016 | Unobligated FY 2015 carryover funds will be swept for redistribution after January 31, 2016. |
| States complete initial eligibility determinations and ranking. Enter all eligible applications into NEST, including ALE funded and substitute parcels. | March 1, 2016 | All eligible applications received by the application cutoff date must be ranked and prioritized. Ranking scores for eligible applications must be input into NEST. |
| Identify projects tentatively select for funding for FY 2016. Submit information to BSNB for easement acquisition funds reservation in FMMI. | March 15, 2016 | Begin preliminary restoration planning on WREs. Prep packages to procure due diligence and easement valuation items. |
| Procure due diligence and easement valuation items. Note: It is critical that WRE appraisals and appraisal technical reviews be contracted for at the same time. | March 25, 2016 | Procure environmental record searches (ALE and WRE), title commitments for WRE, appraisal technical reviews for ALE, and where applicable, individual USPAP appraisals and appraisal technical reviews for WRE. Also, procure FY 2017 AWMAs for WRE, if needed. |
| Submit ACEP waiver request packages requiring NHQ review (24-month ownership), and any new ACEP-WRE Exhibit Es. | April 1, 2016 | Packages will be reviewed in the order submitted. Earlier submittal allows for faster review. Late or incomplete packages will not be reviewed until after completed packages, as time allows. |
| Complete funds assessment to submit requests for additional funding in FY 2016. | April 15, 2016 | Guidance will be provided in FY 2016 regarding the mid-year funds assessment. Fund returns should be submitted through the Allowance Change Tool (ACT) as soon as it is known the funds are not needed, do not wait for the funds assessment. |
| For applications that require national-level internal control review: Complete State-level first- and second-level reviews, upload documents and submit NEST maintenance request for national-level internal control review. | April 29, 2016 | All required documents for applications with obligations above the national-level review threshold must be uploaded into NEST by this date. Earlier submittal allows for faster review. |
| Upload draft, unexecuted ACEP-ALE cooperative agreement. | May 13, 2016 | Cooperative agreements above the grants and agreements review threshold must be submitted to Grants and Agreements for review. Specific instruction on submitting FY2016 ACEP-ALE agreements will be provided in forthcoming guidance. |
| Contracts in place for FY 2017 AWMAs for ACEP-WRE. | June 1, 2016 | States that will use an AWMA for ACEP-WRE in FY 2017 have the contract in place by June 1, 2016 and notify EPD by June 8, 2016 |
| Complete reviews of due diligence and title search documents to make final determinations regarding eligibility and enrollment or deferral for FY 2016. | June 15, 2016 | If hazardous substance issues, title or access issues, onsite or offsite issues, or ALE cooperative agreement or deed terms issues are identified that present eligibility concerns that cannot be readily resolved by the landowner or ALE entity, the application must be deferred or determined ineligible accordingly. |
| Approved ACEP-ALE cooperative agreements, ACE-WRE Exhibit Es, NHQ ACEP waiver decisions. | June 15, 2016 | States will be notified of late, incomplete, or non-compliant submittals that must be deferred until FY 2017. |
| Complete all State-level first- and second-level internal control reviews for those not requiring national level internal controls review. All funds reservation requests to BSNB for subsequently selected applications. | June 22, 2016 | For projects that do not require NHQ review, States may issue offers earlier with notice to the applicant that NRCS will only execute agreements after eligibility determinations and preliminary due diligence reviews are satisfactory and completed. |
| States issue offers of enrollment (agreements) to selected eligible landowners and eligible entities. | June 22, 2016 | For WRE: Finalize the preliminary WRPOs and cost estimates, complete the preliminary obligation of restoration fund supplement to the agreement. |
| Complete enrollment activities, submit information to NAPST for obligation of funds in FMMI, and create agreements in NEST. | July 15, 2016 | States must provide obligating documents to the NAPST following the customer guides. States coordinate with BSNB to remove any funds reservations for applications that will not move forward in FY 2016. |
| Closing deadline for all extended FY 2014 ACEP-WRE enrollments. Extension deadline all FY 2015 ACEP-WRE enrollments. | August, 31 2016 | All FY 2014 ACEP-WRE agreements that were granted an extension will automatically expire on August 31, 2016, and must be closed prior to this date or funds will be deobligated. |
| Submission of FY 2017 easement compensation packages for ACEP-WRE to the EPD SharePoint site in the State folder at “FY 2017 GARCs-ACEP-WRE”. | September 1, 2016 | FY 2017 ACEP-WRE easement compensation packages must be submitted by all States, regardless of whether AWMA or individual USPAP appraisals will be used. |
| States complete NEST entry of all FY 2016 ACEP applications, selected and not selected. | September 16, 2016 | All application statuses must be set as outlined in applicable NEST guidance. |
| Final obligation deadline. | ESTIMATED: September 23, 2016 | Date is subject to change depending on FY 2016 deadlines established by NAPST. |
| Cooperative agreement expiration deadline for FY 2014 ACEP-ALE cooperative agreements. | September 30, 2016 | FY 2014 ACEP-ALE cooperative agreements automatically expire on this date unless an extension (to September 30, 2017) is executed prior to expiration. |

* States are encouraged to complete ACEP new enrollment actions as soon as possible, but, at a minimum, the actions described (including the preparation, submission, review, or execution of all required documentation) must be completed by the identified completion date.